## Q2 1617
The Dudley Group NHS Foundation Trust Performance in Deliver Quarter 2 2016/17
Id | Research Ethics Committee Ref Number | Integrated Research Application System Number | Name of Trial | Target Number of Patients Agreed? | Minimum number agreed | Maximum Number Agreed | Target Date to Recruit Patients Agreed? | Date Agreed to Recruit Target Number of Patients | Total Number of Patients Recruited at agreed Target date | Date that the trial closed to recruitment | Total number of study participants recruited | Reason for Closure of Trial | Comments
13132 | 12/YH/039 | 111935 | ACCELERATE: Assessment of Clinical Effects of Cholesteryl Ester Transfer Protein Inhibition with Evacetrapib in Patients at a High-Risk for Vascular Outcomes | number agreed | 25 | 50 | date agreed | 31/01/2016 | 27 | 23/01/2016 | 27 | recruitment finished | exceeded initial total of 25
13133 | 14/NE/1103 | 159677 | ORAL STRATEGY Pfizer A3921187; Phase 3b/4 Tofacitinib (CP690,55010)for RA | number agreed | 4 | 5 | date agreed | 2016-02-28 | 2 | 2015-11-06 | 2 | recruitment finished | Extremely fast recruitment elsewhere and seeing fewer suitable RA patients
14892 | 14/NW/1373 | 162110 | RCT of DS-5565 in subjects with fibromyalgia E311 | number agreed | 5 | 5 | not available/not agreed |  | 0 | 2016-01-12 | 0 | recruitment finished | There was a delay in recruitment caused by departure of Sub Investigator. Sponsor required new SI to be in place. Once new SI up to speed, study then closed early.
14893 | 14/NW/1374 | 163963 | Open label study of DS-5565 in subjects with fibromyalgia previously enrolled in E311: E312 | number agreed | 5 | 5 | not available/not agreed |  | 0 | 2016-01-12 | 0 | withdrawn by sponsor | Unable to recruit, due to failure to recruit to E311 study.
14894 | 15/SC/0217 | 173398 | A phase II, randomized, double-blind, placebo-controlled study to evaluate the safety and efficacy of Lebrikizumab in patients with persistent moderate to severe atopic dermatitis that is inadequately controlled by topical corticosteroids | number agreed | 2 | 2 | date agreed | 2015-12-31 | 1 | 31/11/2015 | 1 | recruitment finished | Competitive recruitment; study closed early.
15119 | 13/NW/0463 | 124757 | LP0041-63Risk of SCC on skin treated with Ingenol Mebutate or Imiquimod Cream | number agreed | 7 | 7 | date agreed | 2015-11-01 | 6 | 2016-04-30 | 8 | recruitment finished
15121 | 15/YH/0428 | 188418 | DUAL VIII: A 104-week, multi-centre, multinational, open-label, two-arm parallel, randomised to insulin degludec/liraglutide (IDegLira) vs.insulin glargine therapy in subjects with T2DM | number agreed | 8 | 8 | date agreed | 2016-08-22 | 7 | 2016-08-17 | 7 | recruitment finished | 8th patient lined up for screening within original timeframe but screening closed early. Not permitted to enter screening by sponsor.
15171 | 15/NW/0697 | 183760 | REACH (LPS13931): A twenty-six week, randomized, open-label, 2-arm parallel group real world pragmatic trial to assess the clinical and health outcomes benefit of Toujeo® compared to standard of care insulin for initiating basal insulin in insulin n | number agreed | 6 | 6 | date agreed | 2016-09-27 | 5 | 2016-09-27 | 5 | recruitment finished | Issues with pharmacy set up delayed start of recruitment.
15172 | 15/NW/0698 | 183781 | REGAIN (LPS14060): A randomized, open-label, 2-arm parallel group real world pragmatic trial to assess the clinical and health outcomes benefit of transition to Toujeor in basal insulin treated patients with uncontrolled type 2 diabetes mellitus | number agreed | 6 | 6 | date agreed | 2016-09-27 | 2 | 2016-09-27 | 2 | recruitment finished | Issues with pharmacy set up delayed start of recruitment
15173 | 16/LO/0340 | 197371 | MS AURIEL : A randomized, double-blind, confirmatory trial to evaluate the efficacy, safety and immunogenicity of MSB11022 compared with European Union-Approved Humira in subjects with moderate to severe chronic plaque psoriasis. | number agreed | 2 | 2 | date agreed | 2016-07-31 | 1 | 2016-06-15 | 1 | recruitment finished
15209 | 15/SC/0443 | 173722 | OPTIMISE: CAIN457A3302 Long term clear skin maintenance treatment optimization in patients with moderate to severe chronic plaque psoriasis: A randomized, multicenter, open-label with blinded-assessment, comparative, 52 week study to evaluate the eff | number agreed | 5 | 5 | date agreed | 2016-01-31 | 6 | 2016-02-28 | 6 | recruitment finished